## Total Progress Report
Meter Installation Record (As per Daily work) |  |  |  |  | No. of Meter Installed (As per Types) |  |  | No. of Modification, Regulator & Riser Installed |  |  | Cumulative Number of Shed & Bracket |  |  |  | Commissioning |  | Tag Distribution Record |  | Lad-Seal Distribution Record |  | Emergency Record
[5 empty] | A Type | B Type | C Type | No. of Modification Done (House) | Riser Qty. | Total Regulator | With Shed | With Out Shed | Total House | Total Meter | No. of IC Card Distributed | Total House | Tag. Of Card Dist. Qty | Total House | Total House | Total Lad-Seal | Total No. of Complain Solved (On Site) | Total No. of Call Received (Complain) | Total No. of Complain Solved (Over Phone)
| House | Meter | Cumulative House | Cumulative Meter
JAN |  |  | 187 | 1638 | 56 | 1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FEB |  |  | 714 | 4331 | 454 | 3877 | 0 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MAR |  |  | 481 | 4364 | 17 | 4347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1160 | 1126
APR |  |  | 380 | 3508 | 62 | 3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 1166 | 1082
MAY |  |  | 971 | 7472 | 164 | 7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1673 | 1571
JUN |  |  | 860 | 5903 | 166 | 5737 | 0 | 0 | 0 | 0 | 37 | 0 | 1 | 37 | 2435 | 394 | 2539 | 395 | 394 | 2436 | 165 | 1724 | 1559
JUL |  |  | 821 | 4837 | 124 | 4713 | 0 | 0 | 0 | 0 | 529 | 690 | 175 | 1219 | 3042 | 359 | 2505 | 311 | 352 | 3019 | 134 | 1493 | 1359
AUG |  |  | 814 | 4740 | 189 | 4551 | 0 | 0 | 0 | 0 | 474 | 1066 | 205 | 1540 | 4636 | 546 | 4456 | 531 | 28 | 269 | 123 | 1422 | 1299
SEP |  |  | 1103 | 4147 | 799 | 3348 | 0 | 0 | 0 | 0 | 950 | 1180 | 238 | 2130 | 9962 | 1122 | 7732 | 875 | 0 | 0 | 241 | 1794 | 1553
OCT |  |  | 886 | 4557 | 531 | 4026 | 0 | 0 | 0 | 0 | 46 | 101 | 15 | 147 | 12532 | 2173 | 11634 | 1969 | 0 | 0 | 388 | 2189 | 1801
NOV |  |  | 1086 | 5838 | 537 | 5301 | 0 | 2 | 4 | 0 | 1718 | 2874 | 423 | 4592 | 7895 | 1488 | 4976 | 726 | 0 | 0 | 289 | 2045 | 1756
DEC |  |  |  |  | 660 | 4585
Sub Total |  |  | 8303 | 51335 | 3759 | 52821 | 0 | 3 | 14 | 0 | 3754 | 5911 | 1057 | 9665 | 40512 | 6083 | 33842 | 4807 | 774 | 5724 | 1560 | 14666 | 13106
2024-12-01 | 88 | 266 | 8391 | 51601 |  |  |  | 0 | 0 | 0 | 56 | 117 | 22 | 173 | 312 | 82 | 149 | 42 | 0 | 0 | 17 | 82 | 65
2024-12-02 | 93 | 216 | 8484 | 51817 |  |  |  | 0 | 0 | 0 | 72 | 102 | 16 | 174 | 367 | 59 | 98 | 27 | 0 | 0 | 17 | 79 | 62
2024-12-03 | 81 | 276 | 8565 | 52093 |  |  |  | 0 | 0 | 0 | 106 | 110 | 13 | 216 | 403 | 110 | 0 | 0 | 0 | 0 | 20 | 85 | 65
2024-12-04 | 85 | 303 | 8650 | 52396 |  |  |  | 0 | 0 | 0 | 71 | 129 | 22 | 200 | 321 | 92 | 0 | 0 | 0 | 0 | 7 | 51 | 44
2024-12-05 | 60 | 337 | 8710 | 52733 |  |  |  | 0 | 0 | 0 | 95 | 98 | 23 | 193 | 328 | 70 | 0 | 0 | 0 | 0 | 15 | 78 | 63
2024-12-06 | 0 | 0 | 8710 | 52733 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 65 | 60
2024-12-07 | 65 | 314 | 8775 | 53047 |  |  |  | 0 | 0 | 0 | 37 | 201 | 24 | 238 | 409 | 72 | 0 | 0 | 0 | 0 | 17 | 72 | 55
2024-12-08 | 58 | 239 | 8833 | 53286 |  |  |  | 0 | 0 | 0 | 24 | 170 | 21 | 194 | 385 | 55 | 0 | 0 | 0 | 0 | 15 | 81 | 66
2024-12-09 | 83 | 279 | 8916 | 53565 |  |  |  | 0 | 0 | 0 | 49 | 205 | 21 | 254 | 293 | 102 | 0 | 0 | 0 | 0 | 14 | 79 | 65
2024-12-10 | 58 | 250 | 8974 | 53815 |  |  |  | 0 | 0 | 0 | 79 | 149 | 28 | 228 | 294 | 68 | 0 | 0 | 0 | 0 | 14 | 78 | 64
2024-12-11 | 62 | 328 | 9036 | 54143 |  |  |  | 0 | 0 | 0 | 92 | 147 | 30 | 239 | 222 | 37 | 0 | 0 | 0 | 0 | 7 | 67 | 60
2024-12-12 | 66 | 347 | 9102 | 54490 |  |  |  | 0 | 0 | 0 | 66 | 175 | 26 | 241 | 250 | 23 | 0 | 0 | 0 | 0 | 12 | 82 | 70
2024-12-13 | 0 | 0 | 9102 | 54490 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 57 | 50
2024-12-14 | 44 | 278 | 9146 | 54768 |  |  |  | 0 | 0 | 0 | 76 | 182 | 25 | 258 | 243 | 82 | 151 | 68 | 0 | 0 | 11 | 83 | 72
2024-12-15 | 58 | 300 | 9204 | 55068 |  |  |  | 0 | 0 | 0 | 36 | 95 | 12 | 131 | 171 | 75 | 93 | 61 | 0 | 0 | 10 | 76 | 66
2024-12-16 | 0 | 0 | 9204 | 55068 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 73 | 64
2024-12-17 | 60 | 300 | 9264 | 55368 |  |  |  | 0 | 0 | 0 | 67 | 123 | 27 | 190 | 216 | 89 | 161 | 81 | 0 | 0 | 13 | 87 | 74
2024-12-18 | 76 | 299 | 9340 | 55667 |  |  |  | 0 | 0 | 0 | 239 | 177 | 32 | 416 | 157 | 65 | 150 | 61 | 0 | 0 | 7 | 82 | 75
2024-12-19 | 74 | 292 | 9414 | 55959 |  |  |  | 0 | 0 | 0 | 94 | 253 | 35 | 347 | 119 | 67 | 67 | 49 | 0 | 0 | 15 | 88 | 73
2024-12-20 | 0 | 0 | 9414 | 55959 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 80 | 75
2024-12-21 | 68 | 322 | 9482 | 56281 |  |  |  | 0 | 0 | 0 | 156 | 168 | 40 | 324 | 140 | 55 | 63 | 35 | 0 | 0 | 14 | 87 | 73
2024-12-22 | 86 | 299 | 9568 | 56580 |  |  |  | 0 | 0 | 0 | 76 | 279 | 49 | 355 | 3 | 1 | 554 | 58 | 0 | 0 | 7 | 79 | 72
2024-12-23 | 102 | 325 | 9670 | 56905 |  |  |  | 0 | 0 | 0 | 117 | 267 | 46 | 384 | 0 | 0 | 402 | 43 | 0 | 0 | 16 | 89 | 73
2024-12-24
2024-12-25
2024-12-26
2024-12-27
2024-12-28
2024-12-29
2024-12-30
2024-12-31
| 1367 | 5570 | [5 empty] | 0 | 0 | 0 | 1608 | 3147 | 512 | 4755 | 4633 | 1204 | 1888 | 525 | 0 | 0 | 274 | 1780 | 1506
Total |  |  | 9670 | 56905 | 3759 | 52821 | 0 | 3 | 14 | 0 | 5362 | 9058 | 1569 | 14420 | 45145 | 7287 | 35730 | 5332 | 774 | 5724 | 1834 | 16446 | 14612

## MONTH_WISE_PROGRESS_REPORT
Month | Year | Cumulative House | Cumulative Meter | A Type | B Type | C Type | No. of Modification Done (House) | Riser Qty. | Total Regulator | With Shed | With Out Shed | Total House | Total Meter | No. of IC Card Distributed | Total House(IC) | Tag. Of Card Dist. Qty | Total House(TAG) | Total House (Lad-Seal) | Total Lad-Seal | Total No. of Complain Solved (On Site) | Total No. of Call Received (Complain) | Total No. of Complain Solved (Over Phone) | Akbar Shah | Anowara | Bakolia | Bandar | Bayazid | Boalkhali | Chandgaon | Chawkbazar | Double Mooring | EPZ | Halishahar | Hathazari | Karnaphuli | Khulshi | Kotwali | Mirsharai | Pahartali | Panchlaish | Patenga | Patiya | Sadarghat | Sitakunda | Total Burner Survey | Total Wiring Complete | Left Meter | Number of working days | Cumulative Installed (Based on Daily Average) | Running Installed | Target Line (Ideal Cumulative) | Avarage Meter Installed : | 235.875
JAN | 2024 | 187 | 1638 | 56 | 1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 13 | 87 | 12 | 0 | 0 | 4 | 161 | 0 | 1050 | 0 | 0 | 2 | 0 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 12920 | 1638 | 11282 | 13 | 3134.56 | 1638 | 3430.08
FEB | 2024 | 714 | 4331 | 454 | 3877 | 0 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0 | 7 | 155 | 524 | 0 | 0 | 48 | 257 | 73 | 1447 | 0 | 12 | 4 | 865 | 0 | 303 | 24 | 15 | 0 | 157 | 0 | 14321 | 4331 | 9990 | 21 | 5063.52 | 4331 | 5540.9
MAR | 2024 | 481 | 4364 | 17 | 4347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1160 | 1126 | 212 | 0 | 671 | 73 | 512 | 0 | 83 | 10 | 340 | 0 | 606 | 0 | 0 | 588 | 426 | 0 | 487 | 318 | 0 | 0 | 39 | 0 | 14072 | 4364 | 9708 | 20 | 4822.4 | 4364 | 5277.04
APR | 2024 | 380 | 3508 | 62 | 3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 1166 | 1082 | 6 | 0 | 219 | 20 | 120 | 0 | 890 | 161 | 121 | 0 | 214 | 0 | 0 | 87 | 1 | 0 | 105 | 1490 | 0 | 0 | 10 | 0 | 13959 | 3508 | 10451 | 12 | 2893.44 | 3508 | 3166.23
MAY | 2024 | 971 | 7472 | 164 | 7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1673 | 1571 | 422 | 18 | 976 | 0 | 422 | 0 | 1444 | 322 | 366 | 0 | 795 | 25 | 54 | 145 | 877 | 0 | 780 | 485 | 0 | 62 | 234 | 45 | 10145 | 7472 | 2673 | 22 | 5304.64 | 7472 | 5804.75
JUN | 2024 | 860 | 5903 | 166 | 5737 | 0 | 0 | 0 | 0 | 37 | 0 | 1 | 37 | 2435 | 394 | 2539 | 395 | 394 | 2436 | 165 | 1724 | 1559 | 407 | 0 | 140 | 466 | 456 | 0 | 209 | 95 | 785 | 178 | 1193 | 210 | 0 | 512 | 290 | 0 | 524 | 436 | 0 | 0 | 2 | 0 | 6946 | 5903 | 1043 | 19 | 4581.28 | 5903 | 5013.19
JUL | 2024 | 821 | 4837 | 124 | 4713 | 0 | 0 | 0 | 0 | 529 | 690 | 175 | 1219 | 3042 | 359 | 2505 | 311 | 352 | 3019 | 134 | 1493 | 1359 | 204 | 0 | 485 | 0 | 640 | 0 | 417 | 169 | 63 | 0 | 490 | 0 | 0 | 175 | 504 | 0 | 480 | 742 | 0 | 0 | 472 | 0 | 8339 | 4837 | 3502 | 18 | 4340.16 | 4837 | 4749.34
AUG | 2024 | 814 | 4740 | 189 | 4551 | 0 | 0 | 0 | 0 | 474 | 1066 | 205 | 1540 | 4636 | 546 | 4456 | 531 | 28 | 269 | 123 | 1422 | 1299 | 357 | 0 | 416 | 93 | 536 | 0 | 541 | 203 | 466 | 22 | 358 | 58 | 106 | 220 | 337 | 61 | 352 | 279 | 94 | 32 | 80 | 129 | 6664 | 4740 | 1924 | 19 | 4581.28 | 4740 | 5013.19
SEP | 2024 | 1103 | 4147 | 799 | 3348 | 0 | 0 | 0 | 0 | 950 | 1180 | 238 | 2130 | 9962 | 1122 | 7732 | 875 | 0 | 0 | 241 | 1794 | 1553 | 240 | 0 | 260 | 56 | 289 | 18 | 376 | 110 | 409 | 37 | 326 | 499 | 61 | 76 | 368 | 5 | 315 | 312 | 85 | 52 | 210 | 43 | 5649 | 4147 | 1502 | 25 | 6028 | 4147 | 6596.31
OCT | 2024 | 886 | 4557 | 531 | 4026 | 0 | 0 | 0 | 0 | 46 | 101 | 15 | 147 | 12532 | 2173 | 11634 | 1969 | 0 | 0 | 388 | 2189 | 1801 | 203 | 15 | 312 | 89 | 407 | 0 | 316 | 62 | 1085 | 22 | 550 | 165 | 2 | 107 | 282 | 22 | 390 | 304 | 20 | 27 | 146 | 32 | 1170 | 4557 | -3387 | 24 | 5786.88 | 4557 | 6332.45
NOV | 2024 | 1086 | 5838 | 537 | 5301 | 0 | 2 | 4 | 0 | 1718 | 2874 | 423 | 4592 | 7895 | 1488 | 4976 | 726 | 0 | 0 | 289 | 2045 | 1756 | 256 | 0 | 168 | 64 | 146 | 264 | 261 | 74 | 1003 | 54 | 268 | 143 | 0 | 1463 | 607 | 0 | 188 | 335 | 0 | 0 | 452 | 23 | 6255 | 3124 | 3131 | 25 | 6028 | 5838 | 6596.31
DEC | 2024 | 1367 | 5570 | 660 | 4585 | 0 |  |  |  | 1608 | 3147 | 512 | 4755 | 4633 | 1204 | 1888 | 525 | 0 | 0 | 274 | 1780 | 1506 | 476 | 24 | 117 | 588 | 249 | 843 | 171 | 92 | 347 | 65 | 137 | 190 | 27 | 412 | 193 | 3 | 477 | 313 | 12 | 93 | 53 | 31 | 1109 | 313 | 796 | 18 | 4340.16 | 5570 | 4749.34
JAN | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FEB | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MAR | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
APR | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MAY | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
JUN | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
JUL | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AUG | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SEP | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OCT | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11420 | 0 | 11420 | 0 | 0 | 0 | 0
NOV | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12848 | 0 | 12848 | 0 | 0 | 0 | 0
DEC | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12072 | 0 | 12072 | 0 | 0 | 0 | 0
JAN | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FEB | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MAR | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
APR | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MAY | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
JUN | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | apr | 21
[6 empty] | may | 24
[6 empty] | jun | 19
315

## Pivot_analysis
TOTAL METER AND HOUSE INFO. |  |  |  | TOTAL TYPE OF METER INFO. |  |  |  |  | TOTAL RISER CONSTRUCTION INFO. |  |  |  |  | TOTAL SHED INFO | [7 empty] | TOTAL COMMISSIONING INFO |  |  |  |  | TOTAL TAG INFO |  |  |  |  | TOTAL Lad-Seal HOUSE INFO. |  |  |  |  | TOTAL EMERGENCY RECORD
Row Labels | Sum of Cumulative House | Sum of Cumulative Meter |  | Row Labels | Sum of Year | Sum of A Type | Sum of B Type | Sum of C Type | Row Labels | Sum of No. of Modification Done (House) | Sum of Riser Qty. | Sum of Total Regulator |  | Row Labels | Sum of Year | Sum of With Shed | Sum of With Out Shed | Sum of Total House | Sum of Total Meter |  |  | Row Labels | Sum of Year | Sum of No. of IC Card Distributed | Sum of Total House(IC) |  | Row Labels | Sum of Year | Sum of Tag. Of Card Dist. Qty | Sum of Total House(TAG) |  | Row Labels | Sum of Year | Sum of Total House (Lad-Seal) | Sum of Total Lad-Seal |  | Row Labels | Sum of Year | Sum of Total No. of Complain Solved (On Site) | Sum of Total No. of Call Received (Complain) | Sum of Total No. of Complain Solved (Over Phone) |  | Row Labels | Sum of Year | Sum of Akbar Shah | Sum of Anowara | Sum of Bakolia | Sum of Bandar | Sum of Bayazid | Sum of Boalkhali | Sum of Chandgaon | Sum of Chawkbazar | Sum of Double Mooring | Sum of EPZ | Sum of Halishahar | Sum of Hathazari | Sum of Karnaphuli | Sum of Khulshi | Sum of Kotwali | Sum of Mirsharai | Sum of Pahartali | Sum of Panchlaish | Sum of Patenga | Sum of Patiya | Sum of Sadarghat | Sum of Sitakunda | Row Labels | Sum of Total Burner Survey | Sum of Total Wiring Complete | Row Labels | Sum of Number of working days | Sum of Cumulative Installed (Based on Daily Average) | Sum of Running Installed | Sum of Target Line (Ideal Cumulative)
JAN | 187 | 1638 | 9670 | 2023 | 24276 | 0 | 0 | 0 | JAN | 0 | 0 | 0 | 14 | 2023 | 24276 | 0 | 0 | 0 | 0 | shed | 5362 | 2023 | 24276 | 0 | 0 |  | 2023 | 24276 | 0 | 0 |  | 2023 | 24276 | 0 | 0 |  | 2023 | 24276 | 0 | 0 | 0 |  | 2023 | 24276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 36340 | 0 | 2023 | 0 | 0 | 0 | 0
FEB | 714 | 4331 |  | JAN | 2023 | 0 | 0 | 0 | 2023 | 0 | 0 | 0 | 3 | JAN | 2023 | 0 | 0 | 0 | 0 | w/o shed | 9058 | JAN | 2023 | 0 | 0 |  | JAN | 2023 | 0 | 0 |  | JAN | 2023 | 0 | 0 |  | JAN | 2023 | 0 | 0 | 0 |  | JAN | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | JAN | 0 | 0 | JAN | 0 | 0 | 0 | 0
MAR | 481 | 4364 |  | FEB | 2023 | 0 | 0 | 0 | 2024 | 0 | 0 | 0 | 0 | FEB | 2023 | 0 | 0 | 0 | 0 | house | 1569 | FEB | 2023 | 0 | 0 |  | FEB | 2023 | 0 | 0 |  | FEB | 2023 | 0 | 0 |  | FEB | 2023 | 0 | 0 | 0 | 16446 | FEB | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FEB | 0 | 0 | FEB | 0 | 0 | 0 | 0
APR | 380 | 3508 | 56905 | MAR | 2023 | 0 | 0 | 0 | 2025 | 0 | 0 | 0 |  | MAR | 2023 | 0 | 0 | 0 | 0 | meter | 14420 | MAR | 2023 | 0 | 0 |  | MAR | 2023 | 0 | 0 | 5332 | MAR | 2023 | 0 | 0 |  | MAR | 2023 | 0 | 0 | 0 |  | MAR | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MAR | 0 | 0 | MAR | 0 | 0 | 0 | 0
MAY | 971 | 7472 |  | APR | 2023 | 0 | 0 | 0 | FEB | 1 | 10 | 0 |  | APR | 2023 | 0 | 0 | 0 | 0 |  |  | APR | 2023 | 0 | 0 |  | APR | 2023 | 0 | 0 |  | APR | 2023 | 0 | 0 | 774 | APR | 2023 | 0 | 0 | 0 | 1834 | APR | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | APR | 0 | 0 | APR | 0 | 0 | 0 | 0
JUN | 860 | 5903 |  | MAY | 2023 | 0 | 0 | 0 | 2023 | 0 | 0 | 0 |  | MAY | 2023 | 0 | 0 | 0 | 0 |  |  | MAY | 2023 | 0 | 0 | 7287 | MAY | 2023 | 0 | 0 |  | MAY | 2023 | 0 | 0 | 5724 | MAY | 2023 | 0 | 0 | 0 |  | MAY | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MAY | 0 | 0 | MAY | 0 | 0 | 0 | 0
JUL | 821 | 4837 |  | JUN | 2023 | 0 | 0 | 0 | 2024 | 1 | 10 | 0 |  | JUN | 2023 | 0 | 0 | 0 | 0 |  |  | JUN | 2023 | 0 | 0 |  | JUN | 2023 | 0 | 0 | 35730 | JUN | 2023 | 0 | 0 |  | JUN | 2023 | 0 | 0 | 0 | 14612 | JUN | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | JUN | 0 | 0 | JUN | 0 | 0 | 0 | 0
AUG | 814 | 4740 |  | JUL | 2023 | 0 | 0 | 0 | 2025 | 0 | 0 | 0 |  | JUL | 2023 | 0 | 0 | 0 | 0 |  |  | JUL | 2023 | 0 | 0 |  | JUL | 2023 | 0 | 0 |  | JUL | 2023 | 0 | 0 |  | JUL | 2023 | 0 | 0 | 0 |  | JUL | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | JUL | 0 | 0 | JUL | 0 | 0 | 0 | 0 | 236
SEP | 1103 | 4147 |  | AUG | 2023 | 0 | 0 | 0 | MAR | 0 | 0 | 0 |  | AUG | 2023 | 0 | 0 | 0 | 0 |  |  | AUG | 2023 | 0 | 0 | 45145 | AUG | 2023 | 0 | 0 |  | AUG | 2023 | 0 | 0 |  | AUG | 2023 | 0 | 0 | 0 |  | AUG | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | AUG | 0 | 0 | AUG | 0 | 0 | 0 | 0 | 56904.32
OCT | 886 | 4557 |  | SEP | 2023 | 0 | 0 | 0 | 2023 | 0 | 0 | 0 |  | SEP | 2023 | 0 | 0 | 0 | 0 |  |  | SEP | 2023 | 0 | 0 |  | SEP | 2023 | 0 | 0 |  | SEP | 2023 | 0 | 0 |  | SEP | 2023 | 0 | 0 | 0 |  | SEP | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEP | 0 | 0 | SEP | 0 | 0 | 0 | 0 | 56905
NOV | 1086 | 5838 |  | OCT | 2023 | 0 | 0 | 0 | 2024 | 0 | 0 | 0 |  | OCT | 2023 | 0 | 0 | 0 | 0 |  |  | OCT | 2023 | 0 | 0 |  | OCT | 2023 | 0 | 0 |  | OCT | 2023 | 0 | 0 |  | OCT | 2023 | 0 | 0 | 0 |  | OCT | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OCT | 11420 | 0 | OCT | 0 | 0 | 0 | 0 | 62269.13
DEC | 1367 | 5570 |  | NOV | 2023 | 0 | 0 | 0 | 2025 | 0 | 0 | 0 |  | NOV | 2023 | 0 | 0 | 0 | 0 |  |  | NOV | 2023 | 0 | 0 |  | NOV | 2023 | 0 | 0 |  | NOV | 2023 | 0 | 0 |  | NOV | 2023 | 0 | 0 | 0 |  | NOV | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOV | 12848 | 0 | NOV | 0 | 0 | 0 | 0
Grand Total | 9670 | 56905 |  | DEC | 2023 | 0 | 0 | 0 | APR | 0 | 0 | 0 |  | DEC | 2023 | 0 | 0 | 0 | 0 |  |  | DEC | 2023 | 0 | 0 |  | DEC | 2023 | 0 | 0 |  | DEC | 2023 | 0 | 0 |  | DEC | 2023 | 0 | 0 | 0 |  | DEC | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DEC | 12072 | 0 | DEC | 0 | 0 | 0 | 0
|  |  |  | 2024 | 24288 | 3759 | 52821 | 0 | 2023 | 0 | 0 | 0 |  | 2024 | 24288 | 5362 | 9058 | 1569 | 14420 |  |  | 2024 | 24288 | 45145 | 7287 |  | 2024 | 24288 | 35730 | 5332 |  | 2024 | 24288 | 774 | 5724 |  | 2024 | 24288 | 1834 | 16446 | 14612 |  | 2024 | 24288 | 3279 | 57 | 3784 | 1691 | 4313 | 1125 | 4708 | 1350 | 5403 | 451 | 7434 | 1290 | 262 | 3791 | 4750 | 91 | 4655 | 5038 | 226 | 266 | 1855 | 303 | 2024 | 101549 | 48934 | 2024 | 236 | 56904.32 | 56905 | 62269.13
|  |  |  | JAN | 2024 | 56 | 1582 | 0 | 2024 | 0 | 0 | 0 |  | JAN | 2024 | 0 | 0 | 0 | 0 |  |  | JAN | 2024 | 0 | 0 |  | JAN | 2024 | 0 | 0 |  | JAN | 2024 | 0 | 0 |  | JAN | 2024 | 0 | 0 | 0 |  | JAN | 2024 | 56 | 0 | 13 | 87 | 12 | 0 | 0 | 4 | 161 | 0 | 1050 | 0 | 0 | 2 | 0 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | JAN | 12920 | 1638 | JAN | 13 | 3134.56 | 1638 | 3430.08
|  |  |  | FEB | 2024 | 454 | 3877 | 0 | 2025 | 0 | 0 | 0 |  | FEB | 2024 | 0 | 0 | 0 | 0 |  |  | FEB | 2024 | 10 | 1 |  | FEB | 2024 | 0 | 0 |  | FEB | 2024 | 0 | 0 |  | FEB | 2024 | 0 | 0 | 0 |  | FEB | 2024 | 440 | 0 | 7 | 155 | 524 | 0 | 0 | 48 | 257 | 73 | 1447 | 0 | 12 | 4 | 865 | 0 | 303 | 24 | 15 | 0 | 157 | 0 | FEB | 14321 | 4331 | FEB | 21 | 5063.52 | 4331 | 5540.9
|  |  |  | MAR | 2024 | 17 | 4347 | 0 | MAY | 0 | 0 | 0 |  | MAR | 2024 | 0 | 0 | 0 | 0 |  |  | MAR | 2024 | 0 | 0 |  | MAR | 2024 | 0 | 0 |  | MAR | 2024 | 0 | 0 |  | MAR | 2024 | 34 | 1160 | 1126 |  | MAR | 2024 | 212 | 0 | 671 | 73 | 512 | 0 | 83 | 10 | 340 | 0 | 606 | 0 | 0 | 588 | 426 | 0 | 487 | 318 | 0 | 0 | 39 | 0 | MAR | 14072 | 4364 | MAR | 20 | 4822.4 | 4364 | 5277.04
|  |  |  | APR | 2024 | 62 | 3446 | 0 | 2023 | 0 | 0 | 0 |  | APR | 2024 | 0 | 0 | 0 | 0 |  |  | APR | 2024 | 0 | 0 |  | APR | 2024 | 0 | 0 |  | APR | 2024 | 0 | 0 |  | APR | 2024 | 84 | 1166 | 1082 |  | APR | 2024 | 6 | 0 | 219 | 20 | 120 | 0 | 890 | 161 | 121 | 0 | 214 | 0 | 0 | 87 | 1 | 0 | 105 | 1490 | 0 | 0 | 10 | 0 | APR | 13959 | 3508 | APR | 12 | 2893.44 | 3508 | 3166.23
|  |  |  | MAY | 2024 | 164 | 7308 | 0 | 2024 | 0 | 0 | 0 |  | MAY | 2024 | 0 | 0 | 0 | 0 |  |  | MAY | 2024 | 0 | 0 |  | MAY | 2024 | 0 | 0 |  | MAY | 2024 | 0 | 0 |  | MAY | 2024 | 102 | 1673 | 1571 |  | MAY | 2024 | 422 | 18 | 976 | 0 | 422 | 0 | 1444 | 322 | 366 | 0 | 795 | 25 | 54 | 145 | 877 | 0 | 780 | 485 | 0 | 62 | 234 | 45 | MAY | 10145 | 7472 | MAY | 22 | 5304.64 | 7472 | 5804.75
|  |  |  | JUN | 2024 | 166 | 5737 | 0 | 2025 | 0 | 0 | 0 |  | JUN | 2024 | 37 | 0 | 1 | 37 |  |  | JUN | 2024 | 2435 | 394 |  | JUN | 2024 | 2539 | 395 |  | JUN | 2024 | 394 | 2436 |  | JUN | 2024 | 165 | 1724 | 1559 |  | JUN | 2024 | 407 | 0 | 140 | 466 | 456 | 0 | 209 | 95 | 785 | 178 | 1193 | 210 | 0 | 512 | 290 | 0 | 524 | 436 | 0 | 0 | 2 | 0 | JUN | 6946 | 5903 | JUN | 19 | 4581.28 | 5903 | 5013.19
|  |  |  | JUL | 2024 | 124 | 4713 | 0 | JUN | 0 | 0 | 0 |  | JUL | 2024 | 529 | 690 | 175 | 1219 |  |  | JUL | 2024 | 3042 | 359 |  | JUL | 2024 | 2505 | 311 |  | JUL | 2024 | 352 | 3019 |  | JUL | 2024 | 134 | 1493 | 1359 |  | JUL | 2024 | 204 | 0 | 485 | 0 | 640 | 0 | 417 | 169 | 63 | 0 | 490 | 0 | 0 | 175 | 504 | 0 | 480 | 742 | 0 | 0 | 472 | 0 | JUL | 8339 | 4837 | JUL | 18 | 4340.16 | 4837 | 4749.34
|  |  |  | AUG | 2024 | 189 | 4551 | 0 | 2023 | 0 | 0 | 0 |  | AUG | 2024 | 474 | 1066 | 205 | 1540 |  |  | AUG | 2024 | 4636 | 546 |  | AUG | 2024 | 4456 | 531 |  | AUG | 2024 | 28 | 269 |  | AUG | 2024 | 123 | 1422 | 1299 |  | AUG | 2024 | 357 | 0 | 416 | 93 | 536 | 0 | 541 | 203 | 466 | 22 | 358 | 58 | 106 | 220 | 337 | 61 | 352 | 279 | 94 | 32 | 80 | 129 | AUG | 6664 | 4740 | AUG | 19 | 4581.28 | 4740 | 5013.19
|  |  |  | SEP | 2024 | 799 | 3348 | 0 | 2024 | 0 | 0 | 0 |  | SEP | 2024 | 950 | 1180 | 238 | 2130 |  |  | SEP | 2024 | 9962 | 1122 |  | SEP | 2024 | 7732 | 875 |  | SEP | 2024 | 0 | 0 |  | SEP | 2024 | 241 | 1794 | 1553 |  | SEP | 2024 | 240 | 0 | 260 | 56 | 289 | 18 | 376 | 110 | 409 | 37 | 326 | 499 | 61 | 76 | 368 | 5 | 315 | 312 | 85 | 52 | 210 | 43 | SEP | 5649 | 4147 | SEP | 25 | 6028 | 4147 | 6596.31
|  |  |  | OCT | 2024 | 531 | 4026 | 0 | 2025 | 0 | 0 | 0 |  | OCT | 2024 | 46 | 101 | 15 | 147 |  |  | OCT | 2024 | 12532 | 2173 |  | OCT | 2024 | 11634 | 1969 |  | OCT | 2024 | 0 | 0 |  | OCT | 2024 | 388 | 2189 | 1801 |  | OCT | 2024 | 203 | 15 | 312 | 89 | 407 | 0 | 316 | 62 | 1085 | 22 | 550 | 165 | 2 | 107 | 282 | 22 | 390 | 304 | 20 | 27 | 146 | 32 | OCT | 1170 | 4557 | OCT | 24 | 5786.88 | 4557 | 6332.45
|  |  |  | NOV | 2024 | 537 | 5301 | 0 | JUL | 0 | 0 | 0 |  | NOV | 2024 | 1718 | 2874 | 423 | 4592 |  |  | NOV | 2024 | 7895 | 1488 |  | NOV | 2024 | 4976 | 726 |  | NOV | 2024 | 0 | 0 |  | NOV | 2024 | 289 | 2045 | 1756 |  | NOV | 2024 | 256 | 0 | 168 | 64 | 146 | 264 | 261 | 74 | 1003 | 54 | 268 | 143 | 0 | 1463 | 607 | 0 | 188 | 335 | 0 | 0 | 452 | 23 | NOV | 6255 | 3124 | NOV | 25 | 6028 | 5838 | 6596.31
|  |  |  | DEC | 2024 | 660 | 4585 | 0 | 2023 | 0 | 0 | 0 |  | DEC | 2024 | 1608 | 3147 | 512 | 4755 |  |  | DEC | 2024 | 4633 | 1204 |  | DEC | 2024 | 1888 | 525 |  | DEC | 2024 | 0 | 0 |  | DEC | 2024 | 274 | 1780 | 1506 |  | DEC | 2024 | 476 | 24 | 117 | 588 | 249 | 843 | 171 | 92 | 347 | 65 | 137 | 190 | 27 | 412 | 193 | 3 | 477 | 313 | 12 | 93 | 53 | 31 | DEC | 1109 | 313 | DEC | 18 | 4340.16 | 5570 | 4749.34
|  |  |  | 2025 | 12150 | 0 | 0 | 0 | 2024 | 0 | 0 | 0 |  | 2025 | 12150 | 0 | 0 | 0 | 0 |  |  | 2025 | 12150 | 0 | 0 |  | 2025 | 12150 | 0 | 0 |  | 2025 | 12150 | 0 | 0 |  | 2025 | 12150 | 0 | 0 | 0 |  | 2025 | 12150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 | 0 | 0 | 2025 | 0 | 0 | 0 | 0
|  |  |  | JAN | 2025 | 0 | 0 | 0 | AUG | 0 | 0 | 0 |  | JAN | 2025 | 0 | 0 | 0 | 0 |  |  | JAN | 2025 | 0 | 0 |  | JAN | 2025 | 0 | 0 |  | JAN | 2025 | 0 | 0 |  | JAN | 2025 | 0 | 0 | 0 |  | JAN | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | JAN | 0 | 0 | JAN | 0 | 0 | 0 | 0
|  |  |  | FEB | 2025 | 0 | 0 | 0 | 2023 | 0 | 0 | 0 |  | FEB | 2025 | 0 | 0 | 0 | 0 |  |  | FEB | 2025 | 0 | 0 |  | FEB | 2025 | 0 | 0 |  | FEB | 2025 | 0 | 0 |  | FEB | 2025 | 0 | 0 | 0 |  | FEB | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FEB | 0 | 0 | FEB | 0 | 0 | 0 | 0
|  |  |  | MAR | 2025 | 0 | 0 | 0 | 2024 | 0 | 0 | 0 |  | MAR | 2025 | 0 | 0 | 0 | 0 |  |  | MAR | 2025 | 0 | 0 |  | MAR | 2025 | 0 | 0 |  | MAR | 2025 | 0 | 0 |  | MAR | 2025 | 0 | 0 | 0 |  | MAR | 2025 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MAR | 0 | 0 | MAR | 0 | 0 | 0 | 0
|  |  |  | APR | 2025 | 0 | 0 | 0 | SEP | 0 | 0 | 0 |  | APR | 2025 | 0 | 0 | 0 | 0 |  |  | APR | 2025 | 0 | 0 |  | APR | 2025 | 0 | 0 |  | APR | 2025 | 0 | 0 |  | APR | 2025 | 0 | 0 | 0 |  | APR | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | APR | 0 | 0 | APR | 0 | 0 | 0 | 0
|  |  |  | MAY | 2025 | 0 | 0 | 0 | 2023 | 0 | 0 | 0 |  | MAY | 2025 | 0 | 0 | 0 | 0 |  |  | MAY | 2025 | 0 | 0 |  | MAY | 2025 | 0 | 0 |  | MAY | 2025 | 0 | 0 |  | MAY | 2025 | 0 | 0 | 0 |  | MAY | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MAY | 0 | 0 | MAY | 0 | 0 | 0 | 0
|  |  |  | JUN | 2025 | 0 | 0 | 0 | 2024 | 0 | 0 | 0 |  | JUN | 2025 | 0 | 0 | 0 | 0 |  |  | JUN | 2025 | 0 | 0 |  | JUN | 2025 | 0 | 0 |  | JUN | 2025 | 0 | 0 |  | JUN | 2025 | 0 | 0 | 0 |  | JUN | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | JUN | 0 | 0 | JUN | 0 | 0 | 0 | 0
|  |  |  | Grand Total | 60714 | 3759 | 52821 | 0 | OCT | 0 | 0 | 0 |  | Grand Total | 60714 | 5362 | 9058 | 1569 | 14420 |  |  | Grand Total | 60714 | 45145 | 7287 |  | Grand Total | 60714 | 35730 | 5332 |  | Grand Total | 60714 | 774 | 5724 |  | Grand Total | 60714 | 1834 | 16446 | 14612 |  | Grand Total | 60714 | 3279 | 57 | 3784 | 1691 | 4313 | 1125 | 4708 | 1350 | 5403 | 451 | 7434 | 1290 | 262 | 3791 | 4750 | 91 | 4655 | 5038 | 226 | 266 | 1855 | 303 | Grand Total | 137889 | 48934 | Grand Total | 236 | 56904.32 | 56905 | 62269.13
[9 empty] | 2023 | 0 | 0 | 0
[9 empty] | 2024 | 0 | 0 | 0
[9 empty] | NOV | 2 | 4 | 0
[9 empty] | 2023 | 0 | 0 | 0
[9 empty] | 2024 | 2 | 4 | 0
[9 empty] | DEC | 0 | 0 | 0
[9 empty] | 2023 | 0 | 0 | 0
[9 empty] | 2024 | 0 | 0 | 0
[9 empty] | Grand Total | 3 | 14 | 0
TOP MONTH WISE HOUSE
[23 empty] | TOP MONTH WISE IC CARD DISTRIBUTED | [14 empty] | MONTH WISE TOP EMERGENCY CALL RECEIVED
| #N/A | #N/A | [20 empty] | 2023 | 24276 | [13 empty] | 2023 | 24276
#REF! | JAN | #REF! | [19 empty] | 1 | 2023 | 24276 | [12 empty] | 1 | 2023 | 24276
| FEB | [20 empty] | 2 | JAN | 2023 | [12 empty] | 2 | JAN | 2023
| MAR | [20 empty] | 2 | FEB | 2023 | [12 empty] | 2 | FEB | 2023
| APR | [20 empty] | 2 | MAR | 2023 | [12 empty] | 2 | MAR | 2023
| MAY | [20 empty] | 2 | APR | 2023 | [12 empty] | 2 | APR | 2023
| JUN | [20 empty] | 2 | MAY | 2023 | [12 empty] | 2 | MAY | 2023
| JUL | [20 empty] | 2 | JUN | 2023 | [12 empty] | 2 | JUN | 2023
| AUG | [20 empty] | 2 | JUL | 2023 | [12 empty] | 2 | JUL | 2023
| SEP | [20 empty] | 2 | AUG | 2023 | [12 empty] | 2 | AUG | 2023
| OCT | [20 empty] | 2 | SEP | 2023 | [12 empty] | 2 | SEP | 2023
| NOV | [20 empty] | 2 | OCT | 2023 | [12 empty] | 2 | OCT | 2023
| DEC | [20 empty] | 2 | NOV | 2023 | [12 empty] | 2 | NOV | 2023
Grand Total
TOP MONTH WISE METER
| MAY | 7472
12 | JAN | 1638
9 | FEB | 4331
8 | MAR | 4364
11 | APR | 3508
1 | MAY | 7472
2 | JUN | 5903
5 | JUL | 4837
6 | AUG | 4740
10 | SEP | 4147
7 | OCT | 4557
3 | NOV | 5838
4 | DEC | 5570

## ANALYSIS (hidden)
[24 empty] | new installed IC Card |  |  |  | DATE | CARD | HOUSE |  |  | new emergency record |  |  |  | date | solve on site | total complain | solve by phone | new No. of Modification, Regulator & Riser Installed |  |  |  | date | No. of Modification Done (House) | Riser Qty. | Total Regulator | Total calls received (Complain) | Problems solved over the phone | Problems solved on-site | total riser Modification calculation |  | Cumulative Number of Shed & Bracket | [12 empty] | TAG RECORD | [7 empty] | LED-SEAL | [7 empty] | THANA WISE TOTAL METER INSTALLATION RECORDS | Thana | Total Meter Installed | SURVEY CALCULATION |  | STATISTICS
[24 empty] | Date | No. of House | Dis. Card |  | 2024-12-23 | 0 | 0 |  |  | date | solve on site | total complain | solve by phone | 2024-12-23 | 16 | 89 | 73 | date | No. of Modification Done (House) | Riser Qty. | Total Regulator | 2024-12-23 | 0 | 0 | 0 | 16446 | 14612 | 1834 | Total Riser | 1000 | date | With Shed | With Out Shed | Total House | Total Meter | new added | 2024-12-23 | 117 | 267 | 46 | 384 | With Shed | 5362 |  | DATE | Tag. Of Card Dist. Qty | Total House | NEW ADDED | 2024-12-23 | 402 | 43 |  | DATE | Total House | Total Lad-Seal | NEW ADDED | 2024-12-23 | 0 | 0 |  | AKBAR SHAH | 3279 | Total surveys conducted | 137889 | TOTAL WORKING DAYS | 236 | total days | 379 | Number of working days | 236 | 236 /379
| Total Installation Meter Analysis |  |  | Total Type of Meter Installation Calculation |  |  |  |  | No. of IC Card Distributed |  |  |  |  | Tag. Of Card Dist. Qty |  |  |  |  | Total Lad House |  |  |  |  | 2024-12-01 | 312 | 82 |  | 140 |  |  |  |  | 2024-12-01 | 17 | 82 | 65 |  |  |  |  | 2024-12-01 | 0 | 0 | 0 | [7 empty] | Total Riser Modification Complete | 14 | 2024-12-01 | 56 | 117 | 22 | 173 | [6 empty] | With Out Shed | 9058 |  | 2024-12-01 | 149 | 42 | [5 empty] | 2024-12-01 | 0 | 0 | [5 empty] | ANOWARA | 57 | Meters with completed wiring | 48934 | TOTAL METER | 100000 | total days works (pivot table) | 236 | Cumulative Installed (Based on Daily Average) | 56904.32
| Total meter | 100000 | 56.9% | Total meter | 100000 |  |  |  | Total IC Card Distr. | 56905 |  |  |  | Total Card for Dist. | 56905 |  |  |  | Total Led House | 56905 |  |  |  | 2024-12-02 | 367 | 59 | [6 empty] | 2024-12-02 | 17 | 79 | 62 |  |  |  |  | 2024-12-02 | 0 | 0 | 0 | [7 empty] | Left Riser Reserve | 986 | 2024-12-02 | 72 | 102 | 16 | 174 | [6 empty] | Total House | 1569 |  | 2024-12-02 | 98 | 27 | [5 empty] | 2024-12-02 | 0 | 0 | [5 empty] | BAKOLIA | 3784 |  |  | INSTALLED METER | 56905 |  |  | Running Installed | 56905
| Total meters installed | 56905 |  | A-Type | 3759 |  |  |  | Total IC cards distributed | 45145 |  |  |  | Total Tags Distributed | 35730 |  |  |  | Total Lad-Seal Distr. | 5724 |  |  |  | 2024-12-03 | 403 | 110 | [6 empty] | 2024-12-03 | 20 | 85 | 65 |  |  |  |  | 2024-12-03 | 0 | 0 | 0 | [9 empty] | 2024-12-03 | 106 | 110 | 13 | 216 | [6 empty] | Total Meter | 14420 |  | 2024-12-03 | 0 | 0 | [5 empty] | 2024-12-03 | 0 | 0 | [5 empty] | BANDAR | 1691 |  |  | LEFT METER | 43095 |  |  | Target Line (Ideal Cumulative) | 62269.13
| Remaining meters for installation | 43095 |  | B-Type | 52821 |  |  |  | IC cards remaining for distribution. | 11760 |  |  |  | Tags remaining for distribution | 21175 |  |  |  | Left. Lad-Seal for Distri. | 51181 |  |  |  | 2024-12-04 | 321 | 92 | [6 empty] | 2024-12-04 | 7 | 51 | 44 |  |  |  |  | 2024-12-04 | 0 | 0 | 0 | [9 empty] | 2024-12-04 | 71 | 129 | 22 | 200 | [9 empty] | 2024-12-04 | 0 | 0 | [5 empty] | 2024-12-04 | 0 | 0 | [5 empty] | BAYAZID | 4313 |  |  | OVERALL AVERAGE METER | 241.12
|  |  |  | C-Type | 0 | [18 empty] | 2024-12-05 | 328 | 70 | [6 empty] | 2024-12-05 | 15 | 78 | 63 |  |  |  |  | 2024-12-05 | 0 | 0 | 0 | [9 empty] | 2024-12-05 | 95 | 98 | 23 | 193 | [9 empty] | 2024-12-05 | 0 | 0 | [5 empty] | 2024-12-05 | 0 | 0 | [5 empty] | BOALKHALI | 1125 |  |  | ONGING AVERAGE METER | 241.1229
|  |  |  | Left Meter | 43420 | [18 empty] | 2024-12-06 | 0 | 0 | [6 empty] | 2024-12-06 | 5 | 65 | 60 |  |  |  |  | 2024-12-06 | 0 | 0 | 0 | [9 empty] | 2024-12-06 | 0 | 0 | 0 | 0 | [9 empty] | 2024-12-06 | 0 | 0 | [5 empty] | 2024-12-06 | 0 | 0 | [5 empty] | CHANDGAON | 4708 |  |  | DAYS NEED FOR END PROJECT (RUNNING AVERAGE) | 179
TOTAL METER: |  | 56905 | [21 empty] | 2024-12-07 | 409 | 72 | [6 empty] | 2024-12-07 | 17 | 72 | 55 |  |  |  |  | 2024-12-07 | 0 | 0 | 0 | [9 empty] | 2024-12-07 | 37 | 201 | 24 | 238 | [9 empty] | 2024-12-07 | 0 | 0 | [5 empty] | 2024-12-07 | 0 | 0 | [5 empty] | CHAWKBAZAR | 1350
[24 empty] | 2024-12-08 | 385 | 55 | [6 empty] | 2024-12-08 | 15 | 81 | 66 |  |  |  |  | 2024-12-08 | 0 | 0 | 0 | [9 empty] | 2024-12-08 | 24 | 170 | 21 | 194 | [9 empty] | 2024-12-08 | 0 | 0 | [5 empty] | 2024-12-08 | 0 | 0 | [5 empty] | DOUBLE MOORING | 5403
[24 empty] | 2024-12-09 | 293 | 102 | [6 empty] | 2024-12-09 | 14 | 79 | 65 |  |  |  |  | 2024-12-09 | 0 | 0 | 0 | [9 empty] | 2024-12-09 | 49 | 205 | 21 | 254 | [9 empty] | 2024-12-09 | 0 | 0 | [5 empty] | 2024-12-09 | 0 | 0 | [5 empty] | EPZ | 451 |  |  | NUMBER OF REMAINING WORKING DAYS | 143
[24 empty] | 2024-12-10 | 294 | 68 | [6 empty] | 2024-12-10 | 14 | 78 | 64 |  |  |  |  | 2024-12-10 | 0 | 0 | 0 | [9 empty] | 2024-12-10 | 79 | 149 | 28 | 228 | [9 empty] | 2024-12-10 | 0 | 0 | [5 empty] | 2024-12-10 | 0 | 0 | [5 empty] | HALISHAHAR | 7434
[24 empty] | 2024-12-11 | 222 | 37 | [6 empty] | 2024-12-11 | 7 | 67 | 60 |  |  |  |  | 2024-12-11 | 0 | 0 | 0 | [9 empty] | 2024-12-11 | 92 | 147 | 30 | 239 | [9 empty] | 2024-12-11 | 0 | 0 | [5 empty] | 2024-12-11 | 0 | 0 | [5 empty] | HATHAZARI | 1290 |  |  | TARGET AVERAGE METER | 263.8522
[5 empty] | NEW INSTALLED METER | [18 empty] | 2024-12-12 | 250 | 23 | [6 empty] | 2024-12-12 | 12 | 82 | 70 |  |  |  |  | 2024-12-12 | 0 | 0 | 0 | [9 empty] | 2024-12-12 | 66 | 175 | 26 | 241 | [9 empty] | 2024-12-12 | 0 | 0 | [5 empty] | 2024-12-12 | 0 | 0 | [5 empty] | KARNAPHULI | 262 |  |  | TOTAL INSTALLED METER | 56905 | LEFT METER | 43095
| Date | no. of house | no. of meter |  | 2024-12-23 | 102 | 325 | [16 empty] | 2024-12-13 | 0 | 0 | [6 empty] | 2024-12-13 | 7 | 57 | 50 |  |  |  |  | 2024-12-13 | 0 | 0 | 0 | [9 empty] | 2024-12-13 | 0 | 0 | 0 | 0 | [9 empty] | 2024-12-13 | 0 | 0 | [5 empty] | 2024-12-13 | 0 | 0 | [5 empty] | KHULSHI | 3791 |  |  | PREDICT AND STATUS | 91385.16
| 2024-12-01 | 88 | 266 | [7 empty] | 2024-12-02 |  | 37 | [10 empty] | 2024-12-14 | 243 | 82 | [6 empty] | 2024-12-14 | 11 | 83 | 72 |  |  |  |  | 2024-12-14 | 0 | 0 | 0 | [9 empty] | 2024-12-14 | 76 | 182 | 25 | 258 | [9 empty] | 2024-12-14 | 151 | 68 | [5 empty] | 2024-12-14 | 0 | 0 | [5 empty] | KOTWALI | 4750
| 2024-12-02 | 93 | 216 | [20 empty] | 2024-12-15 | 171 | 75 | [6 empty] | 2024-12-15 | 10 | 76 | 66 |  |  |  |  | 2024-12-15 | 0 | 0 | 0 | [9 empty] | 2024-12-15 | 36 | 95 | 12 | 131 | [9 empty] | 2024-12-15 | 93 | 61 | [5 empty] | 2024-12-15 | 0 | 0 | [5 empty] | MIRSHARAI | 91 |  |  | IDEAL DAILY AVERAGE = | 301.3636
| 2024-12-03 | 81 | 276 |  |  |  |  | new installed IC Card |  |  | #VALUE! | [12 empty] | 2024-12-16 | 0 | 0 | [6 empty] | 2024-12-16 | 9 | 73 | 64 |  |  |  |  | 2024-12-16 | 0 | 0 | 0 | [9 empty] | 2024-12-16 | 0 | 0 | 0 | 0 | [9 empty] | 2024-12-16 | 0 | 0 | [5 empty] | 2024-12-16 | 0 | 0 | [5 empty] | PAHARTALI | 4655 |  |  | WEIGHTED PROGRESS RATIO = | 80%
| 2024-12-04 | 85 | 303 |  |  |  |  | Date | No. of House | Dis. Card | [13 empty] | 2024-12-17 | 216 | 89 | [6 empty] | 2024-12-17 | 13 | 87 | 74 |  |  |  |  | 2024-12-17 | 0 | 0 | 0 | [9 empty] | 2024-12-17 | 67 | 123 | 27 | 190 | [9 empty] | 2024-12-17 | 161 | 81 | [5 empty] | 2024-12-17 | 0 | 0 | [5 empty] | PANCHLAISH | 5038
| 2024-12-05 | 60 | 337 |  |  |  |  | 2024-12-01 | 312 | 82 | [13 empty] | 2024-12-18 | 157 | 65 | [6 empty] | 2024-12-18 | 7 | 82 | 75 |  |  |  |  | 2024-12-18 | 0 | 0 | 0 | [9 empty] | 2024-12-18 | 239 | 177 | 32 | 416 | [9 empty] | 2024-12-18 | 150 | 61 | [5 empty] | 2024-12-18 | 0 | 0 | [5 empty] | PATENGA | 226
| 2024-12-06 | 0 | 0 |  |  |  |  | 2024-12-02 | 367 | 59 | [13 empty] | 2024-12-19 | 119 | 67 | [6 empty] | 2024-12-19 | 15 | 88 | 73 |  |  |  |  | 2024-12-19 | 0 | 0 | 0 | [9 empty] | 2024-12-19 | 94 | 253 | 35 | 347 | [9 empty] | 2024-12-19 | 67 | 49 | [5 empty] | 2024-12-19 | 0 | 0 | [5 empty] | PATIYA | 266
| 2024-12-07 | 65 | 314 |  |  |  |  | 2024-12-03 | 403 | 110 | [13 empty] | 2024-12-20 | 0 | 0 | [6 empty] | 2024-12-20 | 5 | 80 | 75 |  |  |  |  | 2024-12-20 | 0 | 0 | 0 | [9 empty] | 2024-12-20 | 0 | 0 | 0 | 0 | [9 empty] | 2024-12-20 | 0 | 0 | [5 empty] | 2024-12-20 | 0 | 0 | [5 empty] | SADARGHAT | 1855
| 2024-12-08 | 58 | 239 |  |  |  |  | 2024-12-04 | 321 | 92 | [13 empty] | 2024-12-21 | 140 | 55 | [6 empty] | 2024-12-21 | 14 | 87 | 73 |  |  |  |  | 2024-12-21 | 0 | 0 | 0 | [9 empty] | 2024-12-21 | 156 | 168 | 40 | 324 | [9 empty] | 2024-12-21 | 402 | 43 | [5 empty] | 2024-12-21 | 0 | 0 | [5 empty] | SITAKUNDA | 303
| 2024-12-09 | 83 | 279 |  |  |  |  | 2024-12-05 | 328 | 70 | [13 empty] | 2024-12-22 | 3 | 1 | [6 empty] | 2024-12-22 | 7 | 79 | 72 |  |  |  |  | 2024-12-22 | 0 | 0 | 0 | [9 empty] | 2024-12-22 | 76 | 279 | 49 | 355 | [9 empty] | 2024-12-22 | 554 | 58 | [5 empty] | 2024-12-22 | 0 | 0 | [6 empty] | 56122
| 2024-12-10 | 58 | 250 |  |  |  |  | 2024-12-06 | 0 | 0 | [13 empty] | 2024-12-23 | 0 | 0 | [6 empty] | 2024-12-23 | 16 | 89 | 73 |  |  |  |  | 2024-12-23 | 0 | 0 | 0 | [9 empty] | 2024-12-23 | 117 | 267 | 46 | 384 | [9 empty] | 2024-12-23 | 402 | 43 | [5 empty] | 2024-12-23 | 0 | 0
| 2024-12-11 | 62 | 328 |  |  |  |  | 2024-12-07 | 409 | 72
| 2024-12-12 | 66 | 347 |  |  |  |  | 2024-12-08 | 385 | 55
| 2024-12-13 | 0 | 0 |  |  |  |  | 2024-12-09 | 293 | 102
| 2024-12-14 | 44 | 278 |  |  |  |  | 2024-12-10 | 294 | 68
| 2024-12-15 | 58 | 300 |  |  |  |  | 2024-12-11 | 222 | 37
| 2024-12-16 | 0 | 0 |  |  |  |  | 2024-12-12 | 250 | 23
| 2024-12-17 | 60 | 300 |  |  |  |  | 2024-12-13 | 0 | 0
| 2024-12-18 | 76 | 299 |  |  |  |  | 2024-12-14 | 243 | 82
| 2024-12-19 | 74 | 292 |  |  |  |  | 2024-12-15 | 171 | 75
| 2024-12-20 | 0 | 0 |  |  |  |  | 2024-12-16 | 0 | 0
| 2024-12-21 | 68 | 322 |  |  |  |  | 2024-12-17 | 216 | 89
| 2024-12-22 | 86 | 299 |  |  |  |  | 2024-12-18 | 157 | 65
| 2024-12-23 | 102 | 325 |  |  |  |  | 2024-12-19 | 119 | 67
[8 empty] | 2024-12-20 | 0 | 0
[8 empty] | 2024-12-21 | 140 | 55
[8 empty] | 2024-12-22 | 3 | 1
[8 empty] | 2024-12-23 | 0 | 0
[12 empty] | 2024-12-01 | 17 | 82 | 65
[9 empty] | New Emergency Call Record |  |  | 2024-12-23 | 16 | 89 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Date | solve by phon. | Total Call | Solve on Site
[9 empty] | 2024-12-01 | 17 | 82 | 65
[9 empty] | 2024-12-02 | 17 | 79 | 62
[9 empty] | 2024-12-03 | 20 | 85 | 65
[9 empty] | 2024-12-04 | 7 | 51 | 44
[9 empty] | 2024-12-05 | 15 | 78 | 63
[9 empty] | 2024-12-06 | 5 | 65 | 60
[9 empty] | 2024-12-07 | 17 | 72 | 55
[9 empty] | 2024-12-08 | 15 | 81 | 66
[9 empty] | 2024-12-09 | 14 | 79 | 65
[9 empty] | 2024-12-10 | 14 | 78 | 64
[9 empty] | 2024-12-11 | 7 | 67 | 60
[9 empty] | 2024-12-12 | 12 | 82 | 70
[9 empty] | 2024-12-13 | 7 | 57 | 50
[9 empty] | 2024-12-14 | 11 | 83 | 72
[9 empty] | 2024-12-15 | 10 | 76 | 66
[9 empty] | 2024-12-16 | 9 | 73 | 64
[9 empty] | 2024-12-17 | 13 | 87 | 74
[9 empty] | 2024-12-18 | 7 | 82 | 75
[9 empty] | 2024-12-19 | 15 | 88 | 73
[9 empty] | 2024-12-20 | 5 | 80 | 75
[9 empty] | 2024-12-21 | 14 | 87 | 73
[9 empty] | 2024-12-22 | 7 | 79 | 72
[9 empty] | 2024-12-23 | 16 | 89 | 73
Formulas:
DATE = VLOOKUP(MAX([new installed IC Card, row below]:Z33),[new installed IC Card, row below]:AB33,1,FALSE)
date = VLOOKUP(MAX([new emergency record, row below]:AI33),[new emergency record, row below]:AL33,1,FALSE)
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Dashboard
Meter Installation Record
Commissioning Record
Tag Record
Riser Construction Record
Shed & Bracket Record
Lad-Seal Record
Emergency Record
Total House :
Total Meter Ins. :
9670
56905
Installation of Pre-Paid Gas Meter for
Karnapulli Gas Distribution Company Limited
ONODA.INC (Chittagong Branch)
Total House :
Total Card Dis. :
7287
45145
Total House :
Total Tag Ins.:
5332
35730
Total House :
Total Lad :
774
5724
Solve by Pho :
Solve on Site :
14612
1834
Total Call Rece :
16446
Total Meter :
100000
New Meter Installed
2024-12-23
House :
Meter :
102
325
New IC Card Distributed
2024-12-23
House :
Total Card :
0
0
2024-12-23
Toall call :
Solve By Pho. :
Solve on Site :
89
73
16
Month :
MAY
7472
Meter :
The Month of the Highest Installations
Total R.Q :
Total M. Done :
14
0
Total Regulator :
3
2024-12-23
Total Regulator :
Riser Qunatity :
No of M. Done :
0
0
0
New Led Distributed
2024-12-23
House :
Lad :
0
0
New Tag Record
2024-12-23
House :
Tag :
43
402
AVAREGE METER INSTALLED(DAY)
241.12
2024-12-23
With Shed:
With out Shed:
House:
117
267
46
Meter :
384
Total w/o Shed :
T. H :
9058
1569
Total Shed :
5362
T. M :
14420
New Shed & Bracket
New Riser Con. Com.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
AVERAGE METER INSTALLED:
APPROXIMATELY DAYS NEED FOR END PROJECT (BASED ON D.A):
=
=
TOTAL WORKING DAYS:
=
236 /379
241.1228814
LEFT WORKING DAYS:
=
143
179
IDEAL AVERAGE METER:
=
263.8522427
PROJECTED INSTALLATION (PREDICT):
=
91385.16
WEIGHTED PROGRESS RATIO:
=
80%